## Initial Baseline Schedule
PROJECT SCHEDULE - BASELINE |  |  |  | TEAM NAME | Axon Guidance
CSc 190 and CSc 191 | [8 empty] | DATE approved or updated: | 2009-04-13
| PROJECT WORK PHASES: | Baseline Start Date | Baseline Finish Date |  |  | Completed (Yes / No)
| POS | 2009-03-09 | 2009-04-06 |  |  | Yes | q | No | q
| PMP | 2009-03-27 | 2009-04-15 |  |  | Yes | q | No | q
| SRS | 2009-04-13 | 2009-05-15 |  |  | Yes | q | No | q
| Req'ts Prototypes | 2009-04-13 | 2009-05-01 |  |  | Yes | q | No | q
| Req'ts Meeting | 2009-04-20 | 2009-04-24 |  |  | Yes | q | No | q
| Architectural Design Prototypes | 2009-09-01 | 2009-09-14 |  |  | Yes | q | No | q
| SDS | 2009-09-01 | 2009-09-14 |  |  | Yes | q | No | q
| Baseline CODE | 2009-09-14 | 2009-10-30 |  |  | Yes | q | No | q
| Usability Tests | 2009-10-01 | 2009-10-30 |  |  | Yes | q | No | q
| STS | 2009-09-01 | 2009-09-30 |  |  | Yes | q | No | q
| Testing & STR | 2009-09-30 | 2009-11-03 |  |  | Yes | q | No | q
| UM | 2009-11-16 | 2009-12-07 |  |  | Yes | q | No | q
| Delivery-CD | 2009-12-07 | 2009-12-15 |  |  | Yes | q | No | q
| Delivery Meeting | 2009-12-07 | 2009-12-15 |  |  | Yes | q | No | q

## Baseline Change
PROJECT SCHEDULE - BASELINE CHANGE |  |  |  | TEAM NAME | Axon Guidance
CSc 190 and CSc 191 | [8 empty] | DATE approved or updated: | 2009-09-30
Only indicate changes!
| PROJECT WORK PHASES: | Baseline Start Date | Baseline Finish Date | New Baseline Start Date | New Baseline Finish Date | Completed (Yes / No)
| POS |  |  |  |  | Yes | q | No | q
| PMP |  |  |  |  | Yes | q | No | q
| SRS |  |  |  |  | Yes | q | No | q
| Req'ts Prototypes |  |  |  |  | Yes | q | No | q
| Req'ts Meeting |  |  |  |  | Yes | q | No | q
| Architectural Design Prototypes |  |  |  |  | Yes | q | No | q
| SDS |  |  |  | 2009-10-16 | Yes | q | No | q
| Baseline CODE |  |  |  |  | Yes | q | No | q
| Usability Tests |  |  |  |  | Yes | q | No | q
| STS |  |  |  | 2009-10-23 | Yes | q | No | q
| Testing & STR |  |  |  |  | Yes | q | No | q
| UM |  |  |  |  | Yes | q | No | q
| Delivery-CD |  |  |  |  | Yes | q | No | q
| Delivery Meeting |  |  |  |  | Yes | q | No | q
Reason for the change:
Changed to accommodate Professor Jin's schedule.